## ISM Checklist
Initial Measurements Guidelines |  | Checks
View | Measurements Needed | Elevation A | Elevation B | Elevation C | Elevation D | Elevation E | Elevation F | Elevation G | Elevation H | Elevation I | Elevation J
1. Kitchen top view should contains
A. All the walls ( Kitchen & if any balcony attached to it) | Width of walls
B. Beam | Width & Depth
C. Coloumn | Width & Depth
D. Window | Width,Height,Wall below window bottom height from FFL,Wall above window, wall dimension in left & right of window
E. Door | Width,Height & Wall above doors & wall dimension from the nearest adjacent elevation
2. Elevation View should contains
A. Coloumn | Height & width for front view, Depth & height in section view
B. Beam | Height & width for front view, Depth & height in section view
C. Window | Width,Height,Wall below window bottom height from FFL,Wall above window, wall dimension in left & right of window
D. Door | Width,Height & Wall above doors
E. Sunk Drop | Drop, Width
F. Ceiling height | Ceiling height measurements at 2 to 3 places below Ceiling & Sunk Drop
G. Electrical Point | Height from FFL, Distance from nearest elevation wall
H. Plumbing Points | Height from FFL, Distance from nearest elevation wall
I. Platform | Height & Width
J. Depression | Height,width & Depth
K. Projection | Height,width & Projection
L. Pre-installed countertop | Depth, height & thickness of countertop
M. Concrete Skirting | Depth, height & thickness of countertop
N. Gas Pipeline entry point | Height from floor & distance from the nearest wall
3. Ceiling Measurements
A. Fire Alarm Point | Length from atleat two elevation
B. Electrical point | Length from atleat two elevation
C. water sprinkel points | Length from atleat two elevation
D. False Ceiling | Width & drop
Note: 1. Check Whether all walls is solid or its of gypsum or ply wall.
''''''''''''2. Ask client/customer for electrical & plumbing layout of kitchen (for walls, floor & ceiling).

## Validation Checklist
Site Validation Checksheet
| Date: |  |  |  |  | Client Name:
TO DO LIST
| *All the points mentioned below must be executed & after execution check box must be ticked in & if not done then cross mark the check box. | [5 empty] | Check Box
| Masking of LC as per final design with cabinet name written in it______________________________________________________________________________________________________________ | [6 empty] | Remarks
Masking of UC as per final design with cabinet name written in it_____________________________________________________________________________________________________________
Masking of TT as per final design with cabinet name written in it_______________________________________________________________________________________________________________________
Masking of Loft as per final design with cabinet name written in it________________________________________________________________________________________________________________
Masking of Island as per final design with cabinet name written in it_________________________________________________________________________________________________________________
Kitchen Wall surface level to be checked with 600mm spirit level at 5 to 6 places for one wall_______________________________________________________________________________________________________________________________
Validate
*All the Points mentioned must be validated & if it is correct tick mark the check box & if it is not okay cross mark the check box & write remarks in the coloumn given.
| After masking all cabinet fits in the given space________________________________________________________________________________________________________________________ | [6 empty] | Remarks
Minimum 50mm filler at all space between cabinets and adjacent wall & 100mm between loft & ceiling.___________________________________________________________________________________________________
Minimum 920mm distance between parallel Cabinets _______________________________________________________________________________________________________________
False ceiling drop (if not constructed) must be 100mm above loft cabinet ________________________________________________________________________________________________
Gas pipeline inlet point as per MEP/EPT & Standard defined _____________________________________________________________________________________________________________________
Electrical points as per MEP/EPT & Standard defined (Ref. Table SVC02)________________________________________________________________________________________________
Gas Pipeline flow must not come behind any cabinet___________________________________________________________________________________________________________
Plumbing points as per MEP/EPT & Standard defined (Ref. Table SVC03)________________________________________________________________________________________________
Hood/Chimney Unit must have 10mm or more width then chimney width ___________________________________________________________________________________________________
Chimney width as per Specification___________, actual space left at site____________
Kitchen Wall surface in level _________________________________________________________________________________________________________________________________________
All visible ends of kitchen have end panels in drawing ____________________________________________________________________________________________________________
Lower Cabinet corner unit must be considered 80mm more in width for 630 depth cabinet & 40mm more in width for 590 depth cabinet during masking ( Dead space calculation formula, X+ Cabinet width= Depth of perpendicular cabinet+ 50mm+ Shutter size of corner unit).
Dead Space left between corner unit &wall parallel to it____________
Corner unit wall must be of 90 degree.__________________________________________________________________________________________________________________________________________
Upper Cabinet corner unit must not be less than 800mm __________________________________________________________________________________________________________
For single door fridge 100mm more width space should be left out & for double door fridge 200mm more width space should be left out ___________________________________________________________________________________________________
Fridge width_________, height___________ as per specification. Actual width left___________, height________ for fridge.
Wherever there is UP & Over cabinet there must not be any loft above it( Check appliance unit & UC with UP & over hardware & if there is loft above it.)___________________________________________
End Panel must always be there at each end of frame loft whether it is visible end or not.___________________________________________________________________________________________________
Topline Wardrobe must not have loft above it________________________________________________________________________________________________________________
50mm fillers above wardrobe loft & between walls & Wardrobe ________________________________________________________________________________________________________________
Remarks
Site Validation Checksheet
ETP/MEP Standards
|  | Table SVC01 |  | Table SVC02
|  | Electrical equipment & power needed for it |  | Distance of electrical Points from Vertical panel & FFL
|  | Appliance | Power | Appliance | Height from FFL | Distance from vertical panel of cabinet
|  | Hob | 15 Amp | Hob | 700mm | 200mm
|  | Chimney | 15 Amp | Chimney | 2000mm | In centre of Hood unit
|  | Oven(In Built) | 15 Amp | Oven(In Built) | 800mm | 100mm
|  | Microwave(In Built) | 15 Amp | Microwave(In Built) | 1350mm | 100mm
|  | Light Point | 5 Amp | Light Point | 50mm above UC | 50mm from side wall
|  | Fridge | 15 Amp | Fridge | 1100mm | 200mm
|  | Dishwasher | 15 Amp | Dishwasher | 500mm(in sink unit) | 100mm(in sink unit)
|  | Under Sink RO | 5 Amp | Under Sink RO | 500mm | 100mm
|  | Wall RO | 15 Amp | Wall RO | 2000mm | 100mm
|  | Geyser | 15 Amp | Geyser | as per requirement | 200mm from wall
|  | Wall Microwave | 15 Amp | Wall Microwave | 1650mm | 100mm
|  | Washing Machine | 15 Amp | Washing Machine | 500mm | 100mm
|  | Switch Board | as per requirement | Switch Board | 1100mm | As per requirement
Table SVC03
Distance of Plumbing Points from Vertical panel & FFL
|  |  |  | Appliance | Height from FFL | Distance from vertical panel of cabinet
|  |  |  | Under Sink RO(cold water) | 450mm | 80mm Centre of cabinet
|  |  |  | Under Sink (Hot water) | 450mm | Centre of cabinet
|  |  |  | Under Sink (Cold water) | 450mm | 80mm Centre of cabinet
|  |  |  | Waste water on wall | 350mm | Centre of cabinet
|  |  |  | Wall RO(Inlet) | 1630mm | 100mm from vertical panel of cabinet.
|  |  |  | Wall RO(Outlet) | 1630mm | 150mm from vertical panel of cabinet.
|  |  |  | Dishwasher(Inlet) | 450mm( In sink unit) | 100mm from vertical of sink unit.
|  |  |  | Dishwasher(Outlet) | 350mm (In sink unit) | 150mm from vertical panel of sink unit.
|  |  |  | Wall Sink (Cold) | 1100mm | Centre of cabinet
|  |  |  | Wall Sink (Hot) | 1100mm | 50mm from centre of cabinet
|  |  |  | Washing Machine(Inlet) | 450mm | Centre of cabinet
|  |  |  | Washing Machine(Outlet) | 350mm | 50mm from centre of cabinet
|  |  |  | Geyser(Inlet) | as per requirement | as per requirement
|  |  |  | Geyser(Outlet) | as per requirement | as per requirement
#All the above dimension can vary up to max 80mm from the given standard, although non of the above points can come behind of any of the panel of carcass of cabinet.
Note:
1. Shutter opening need to be checked.
a. If filler is not there shutter will hit the wall.
b. If shutter opening is chimney/fridge side then shutter will bang on appliance.
2. Working & walking space needs to be checked.(Between two parallel counter minimum 3ft space needed, kitchen triangle must be followed, that is perimeter of triangle with sink,hob & fridge at three corner should be minimum 12ft & maximum 26ft.)
3. Island marking, If Island chimney it's hanging point need to checked, hob gas pipeline need to checked for island.
4. If under Counter Chimney is there check its specification and do marking as per specification.( check its motor placement point, exhaust outlet point)
Accessories & document needed for site validation:
1. Final Drawing.
2. Site Measurements report.
3. MEP/EPT Drawing.
4. Laser level tool.
5. Masking tape, Marker/Chalk.
6. Measuring tape.
7. Specification(length,width,height & power needed) of all the appliances in the kitchen( Hob, Chimney, Oven, Microwave,Dishwasher & fridge).
8. Spirit level of 600mm.

## Site readiness checksheet
Date |  | SITE READINESS CHECKSHEET |  |  | Project Name
|  | Safety |  |  | Yes | No | Remarks
| l | Exposed Wire__________________________________________________________________
| ll | Sharp edges, open rods________________________________________________________________
| lll | Balcony without ralling_______________________________________________________________
| lV | Gas pipeline connection with safety measures if applicable_________________________________________
|  | Civil Work |  |  | Yes | No | Remarks
| l | Apartment/flat handed over by builder for interior work______________________________________
| Il | Flooring completed & leveled properly___________________________________________________________
| lll | Walls finished with plastering/putty/1st coat of painting/tiling_________________________________________
| lV | Ceiling done with false ceiling if applicable______________________________________________________________
| V | Stone Avilability for countertop & Dado______________________________________________________________
| VI | Proper installed windows & doors if any present_____________________________________
|  | Electrical & Plumbing |  |  | Yes | No | Remarks
| l | Concealed wiring with provisions for appliance as per layout_______________________________________________________
| ll | Switchboard & sockets as per ETP in final design____________________________________________________________________________
| lll | Water inlet & outlet points fixed as per the ETP in final design______________________________________________________________
|  | Venting & lighting |  |  | Yes | No | Remarks
| l | Chimney duct opening cut-out on wall if applicable as per the final desgn__________________________________________
| ll | Proper lighting should be ensured in the installation area _______________________________
| ll | Gas Pipeline entry point hole & its meter position as per the final design _______________________________
|  | Accessibility |  |  | Yes | No | Remarks
| l | Site free from debris and other construction materials_____________________________________
| ll | Industrial power point within twenty metre of installation area___________________________
| lll | Vehicle access within 10m of installation site; proper passage and good road required____________
| lV | Lift should be there for shifting material above second floor(otherwise it will be charge)______
| V | Clear entry points for bringing in modular units________________________________________
|  | Storage |  |  | Yes | No | Remarks
| l | Temporary dry space for keeping materials & tools(35 sq.ft. needed for a kitchen)____________________________________
| ll | Provision for locking of store area door & windows_____________________________________
|  | Others if applicable |  |  | Yes | No | Remarks
| l | Permission for movement of material through service lift_________________________________
| ll | Other permission if applicable_____________________________________________________
|  | Customer Sign. | __________________ | Supervisor Sign. | __________________________

## LC Carcass Checklist
Date |  | Installation checklist | Project Name
|  | LC Carcass | Check Box | Remarks
| l | Cabinet Position as per final design__________________________________________________________________
| ll | Laser level of cabinet LC top edge________________________________________________________________
| ll | Laser level of LC cabinet bottom edge & TT Bottom edge ________________________________________________________________
| lll | Cabinet top height as per the final design_________________________________________________________________
Cabinet top edge height as per design_____________.
Actual top edge height of cabinet from FFL_____________.
| lV | Skirting height as per final design_________________________________________________________
Skirting height as per design_____________.
Skirting height from FFL_____________.
| V | Gas pipeline provision & flow through cabinet without any obstruction after Countertop installation.(gas pipeline must not be hidden more than 300mm)
| VI | Corner unit blind & shutter opening & its width needs to be checked it must be as per drawing.
| VI(a) | Corner unit C filler installed.
Dead space left between corner unit & wall._________
Space left between corner unit top front edge & cabinet parallel to blind._________
| VII | Dishwasher, Sink plumbing Inlet & Outlet provision & flow of pipe must not have any obstruction during its installation after counter top.
| VIII | Gas Leak detector & Electrical board for hob provision in backpanel if any present at site._________________________________________________________
| IX | Cleaning of floor & removal of floor protection below LC Cabinet before Counter top installation.
| X | Joining member position for sink & hob checked as per equipment____________________________________________________________________
Length (between JM) required for Sink as per specification________ & actual at site___________.
Length (between JM) required for hob as per specification________ & actual at site___________.
| XI | EPT points must not come behind any panels____________________________________________________________
| XII | Visible end leg position_____________________________________________________________________
| XIII | Enough space for Dishwasher & fridge( as per specification of appliances)._____________________________________________________________________
Dishwasher width as per specification_________ Length between all four corners of adjacent cabinet________, _________, _________, _________
Dishwasher height as per specification__________, height of top bottom edge from FFL__________
Checker Sign:
Approver Sign:

## Counter Top & Dado Checklist
Date |  | Installation checklist | Project Name
|  | Countertop & Dado Installation | Check Box | Remarks
| l | Depth of Countertop to be communicated to vendors.__________________________________________________________________
Depth of countertop_______, Molding height________, Water splash height___________
Bar Counter depth_______, Bar Counter height from FFL_______.
| ll | Profile of molding to be communicated ________________________________________________________________
| lll | Waterfall design & if molding is there then thickness of backing to be communicated._________________________________________________________________
Type of waterfall: single stone fall__________ or stone fall with molding___________, if its having molding then thickness of backing & backing needs to installed before stone work starts.
| lV | Joints of countertop & where it is going to come to be communicated_________________________________________________________
| V | Backing on top of cabinet for handle kitchen if mighter molding is there.___________________________________________________________________________________
If backing is provided between LC cabinet top & stone check height of dado to match top edge of UC,TT & Rolling shutter.
| VI | Cutout dimension of hob & sink to be provided along with availability of appliances.____________________________________________________________________
Drawing of sink & hob cutout must be attached in the drawing of countertop with this checklist.
| VII | Drawing for Dado, Cutout points for wall mounted faucet Drawing_______________________________________________________________
| VIII | Electrical points on Dado with module size of electrical board._________________________________________________________
| IX | If grains need to be matched of Dado & Countertop then it should be communicated ______________
Checker Sign:
Approver Sign:
Stone Vendor Sign with:
Customer or its representative sign (if stone work is in customer Scope):
Note: While Sharing this file attach Drawing of Countertop , Dado to stone vendor & in customer group & while placing stone with adhesive below it one video of water flow above the counter needs to be recorded on the counter top.

## UC & Loft checklist
Date |  | Installation checklist | Project Name
|  | Upper & Loft Cabinet | Check Box | Remarks
| I | Cabinet Position as per final design__________________________________________________________________
| ll | EPT must not be behind any panel. ________________________________________________________________
| lII | Chimney centre point alignment with hob centre point.__________________________________________________________________
Length of chimney centre point from one of the nearest wall________. Hob centre point from the same wall___________.
| lV | Backing if any cabinet have projection in hanging wall______________________________________________
| V | Mounting of hanging clip with laser level.___________________________________________________________________________________
| VII | Laser Level of bottom edge of Upper unit.___________________________________________________________________________________
| VIII | Glass shutter cabinet carcass position as per drawing(mounting point of Hinges & Bifold use to be different in Solid & Glass Cabinet).
| IX | Visible end of cabinets should be there at time carcass installation_______________________________________________________________
| X | C Filler must be installed at time of carcass installation_______________________________________________________________
| XI | 13mm screw for mounting glass shutter._____________________________________________________________
| XII | Electrical connection for under cabinet & surface light need to be done before End cabinet installation._____________________________________________________________
| XIII | Chimney Outlet point & its duct flow need to be checked while loft installation._____________________________________________________________
Checker Sign:
Approver Sign:

## Handover checklist
Date |  | Installation checklist | Project Name
|  | Handover Checklist | YES | NO | Remarks
| I | Cabinet position as per final drawing & signoff document__________________________________________________________________
| ll | Scratch or dent on any visible panel.________________________________________________________________
| lII | Cleaning of kitchen(Removal of packaging material, wastage after installation etc)._________________________________________________________________________
| lV | Alignment of shutters as per drawing(Vertical of LC,UC & Loft, Horizontal top & bottom line of LC UC & Loft needs to be checked with laser level.)______________________________________________________
| V | Shutter opening as per drawing.___________________________________________________________________________________
| VI | Appliances( Hob,Chimney,Microwave,Oven & Fridge door opening) functioning well.Under cabinet, Surface & strip lights needs to be inspected for proper operations.
| VII | Handles at proper position as per final design._______________________________________________________________
| VIII | Hardware Cover caps & Clips(for hinges,drawer,bifold,up & over)._____________________________________________________________
| IX | Skirting alignment & proper fixed with legs of cabinet._____________________________________________________________
| X | Screw alignment, Unwanted screw & all screw must not be visible._____________________________________________________________
| XI | Appliances functioning well.Under cabinet, Surface & strip lights needs to be inspected for proper operations.
| XII | Skirting alignment & proper fixed with legs of cabinet._____________________________________________________________
| XIII | Corner Joint of Skirting installed as per requirement._____________________________________________________________
| XIV | Filler finish( No bur,black line on cut side. 2mm gap between shutter & filler, top & bottom edges of filler must match with adjacent shutter of filler)
| XV | All debris & NC material must be removed before handover.___________________________________________________________________
| XVI | Shutter beside chimney must not hit chimney.___________________________________________________________________
Hardware:
| XIV | Soft close of Hinges for all shutter working properly. _______________________________________________________________
| XV | All shutter with hinges must close with speed.______________________________________________________
| XVI | Drawer Soft close working properly._______________________________________________________________
| XVII | Runner with recommended weight capacity must be used at appropriate location.___________________________________
| XVIII | Bi-fold,Up & Over & Lift-Up doesn’t open with jerk._________________________________________________________
| XIX | Bi-fold,Up & Over & Lift-Up stop wherever wanted upto a certain limit..________________________________________________________
| XX | Hardware Cover caps & Clips(for hinges,drawer,bifold,up & over).___________________________________________________________________
Checker Sign:
Approver Sign(Designer):
Client Signature: