## Monthly Executed Projects
Monthly Executed Projects
Experience Centre Location |  |  |  | Ops Manager Name |  | Month'Year
Serial No. | Project Name | Project ID | Handovered date | Total days taken to complete the project | Learning of project
Team Planning for Installation |  | No. of team needed |  | No. of Trained team (In-house & Vendor ) |  | Training Needed for new Vendor( need to be planned between 20th to 5th of next month)
Note:
1. IF LC Carcass is less than 15 in qty consider TT as LC, all the cabinets must be assembled & installed with quality checks in one day
2. Consider two days for countertop & Dado Installation
3. If UC & Loft together less than 15 in quantity must get installed in one day with all quality checks (TAT 1 day)
4. Shutter & Hardware installation in one day with all QC (TAT 1 day)
5. All appliances, lights & remaining alignment work with handover to done in one day (TAT 1 day)
6. Customer adherence to given date severity level should be measured on 1,2 & 3 scale where 1 for Cumpolsory to be adhered, 2 for adherence needed, followup neeeded with customer regarding their site readiness & 3 cold execution at site by customer(need weekly followup from customer). For 1 regerous followup from ISC regarding material delivery & adherence to the time line, for 2 followup with ISC & Customer too. For 3rd inform ISC regarding priority & followup customer.